## Seguimiento Defectos
|  | INSTITUTO TECNOLÓGICO SUPERIOR ZACATECAS OCCIDENTE |  |  | CENTRO DE DESARROLLO DE SOFTWARE E INVESTIGACIÓN
Historias de usuario y criterios de aceptación
Bitácora de defectos
Nombre del Proyecto: |  | RutasOffline
No. Defecto | Fecha creación | Responsable | Descripción del defecto | Historia de Usuario | Fase de proceso | Prioridad | estatus | Resolución | Fecha resolución | Status
1 | 2020-03-24 | NEC | Diseño de la app: Al momento de compilar no se lograba encontrar las imágenes que se estaban utilizando para la bienvenida. | HU1 | Cerrado | Bajo | Cerrado | Se modificaron lor formatos png, ademas se utilizo la librería mipmap para gestionar las imágenes. | 2020-03-25 | New
2 | 2020-04-02 | NEC | Diseño de la app: No se mostraba el menu incorporado. | HU1 | Cerrado | Alto | Cerrado | Se agrego un toolbar a cada layout de la app | 2020-04-06 | Under Review
3 | 2020-04-10 | NEC | Consulta a la base de datos: Error al incorporal la vercion mas reciente de las librerias de Volley | HU1 | Cerrado | Alto | Cerrado | Se opto por utilizar una vercion anterior mas estable. | 2020-04-14 | In Progress
4 | 2020-04-14 | NEC | Consulta a la base de datos: Se encontro un error al intentar de relacionar tablas a la base de datos del cliente. | HU1 | Cerrado | Alto | Cerrado | Se creo una nueva tabla solo con la informacion necesaria. | 2020-04-15 | Completed
5 | 2020-04-17 | NEC | Consulta a la base de datos: Al hacer una consulta no se agregaban todos los datos necesarios al JSON que se esta utilizando. | HU1 | Cerrado | Alto | Cerrado | Se modificaron variables en el web service php. | 2020-04-17
6 | 2020-04-21 | NEC | Consulta a la base de datos: No se lograban agregar valores a la base de datos que contaran con acentos. | HU1 | Cerrado | Alto | Cerrado | Se modificaron los atrivutos de la tabla a la que se hacia la consulta | 2020-04-21
7 | 2020-04-29 | NEC | Funcionamiento de la app: No se lograban agregar valores a la base de datos que contaran con acentos. | HU1 | Cerrado | Medio | Cerrado | Se incorporo el formato UTF 8 a la aplicación. | 2020-04-30
Note on F13: Choose from the drop down box.
Note on G13: Choose from the drop down list

## Instrucciones Defectlog
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).